## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 59 | 28.5 |  |  |  | 14 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-11-02 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-17 | 2016-10-19 | 2016-10-21 | 2016-10-24 | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Set up note drop | EE |  | 4 | 4 |  |  | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Assigned
6 | 2 | Set up event system | EE |  | 4 | 1 |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Active
7 | [25 empty] | Verify?
5 | 1 | set up super spring | EE |  | 1 | 1 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 2 | create a level | EE |  | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Deferred
5 | 1 | Set up spring board | EE |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
6 | 2 | set up arrangement compare | EE |  | 4 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Can't Repro
12
5 | 1 | Set up conveyer belt | EE |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2 | set up forward momentum | EE |  | 4 | 0 |  |  | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15
5 | 1 | Setup prefab and drop onto screen from ui | EE |  | 4 | 4 |  |  | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | create a working wining system for showing off game. | EE |  | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1 | Set up audio file | EE |  | 1 | 1 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | set up audio getting triggered | EE |  | 2 | 2 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | set up layers and colliders | EE |  | 1 | 1 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Make new levels | ALL |  | 10 | 0 |  |  | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | Make a couple new mechanics to add to the game.
23 | 1 | Side scroll or backwards conveyer?
24 | 1 | 16th note add?
25 | 1 | Longer note hold?
26 | 2 | Make UI better | EE |  | 2 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
27 | 1 | Make intro levels really teach | EE |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1 | Set Up level Components | EE |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | Add all audio | EE |  | 1 | 0.5 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
30 | 2 | Bugs | EE |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 59 | 59 | 50.5714 | 42.1429 | 29.5 | 21.0714 | 12.6429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 39 | 39 | 39 | 22 | 22 | 17 | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
216 |  |  | 2 | [5 empty] | 20 | 20 | 20 | 16 | 11 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
217 |  |  | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Eliana Abraham | EE |  |  |  |  | EE | 49 | 49 | 49 | 28 | 23 | 19 | 19 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
223 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
236

## Daily Scrum
Producer | 2016-11-02 |  | Team Members
Approved | Dates |  | Eliana Abraham
| 2016-10-17 | Mon | Done: Tried to think of a game Next: Working on previous project Help: Nothing now | Done: Planned X Next: Implement X Help: — | Done: Tried to think of a game Next: Working on previous project Help: Nothing now
| 2016-10-18 | Tue | Done: Have a really good idea for a game Next: Working on previous project Help: Nothing now |  | Done: Have a really good idea for a game Next: Working on previous project Help: Nothing now
| 2016-10-19 | Wed | Done: Nothing yet Next: Create the components of my game Help: Feedback about my idea |  | Done: Nothing yet Next: Create the components of my game Help: Feedback about my idea
| 2016-10-20 | Thu | Done: Drew out the ideas for components. Made assets and prefabs. set up sprites and simple audio. added physics. and physics materials. set up colliders Next: Make scripts for my components Help: — |  | Done: Drew out the ideas for components. Made assets and prefabs. set up sprites and simple audio. added physics. and physics materials. set up colliders Next: Make scripts for my components Help: —
| 2016-10-21 | Fri | Done: Finished component scripts. Made them moveable. Set up all of the moveable pieces. made a simple event system. Made a simple UI Next: set up pieces for game play. Help: — |  | Done: Finished component scripts. Made them moveable. Set up all of the moveable pieces. made a simple event system. Made a simple UI Next: set up pieces for game play. Help: —
| 2016-10-22 | Sat | Done: I attempted to do as much as I could but I got into an accident. Next: recover Help: — |  | Done: I attempted to do as much as I could but I got into an accident. Next: recover Help: —
| 2016-10-23 | Sun | Done: Still in recovery. Arm is numb. can't type Next: recover Help: — |  | Done: Still in recovery. Arm is numb. can't type Next: recover Help: —
| 2016-10-24 | Mon | Done: Panic, attach analysis, attach other docs, I didn't end up having time for a submission. Also didn't have much to turn in because of injury Next: recovering, then continue Help: — |  | Done: Panic, attach analysis, attach other docs, I didn't end up having time for a submission. Also didn't have much to turn in because of injury Next: recovering, then continue Help: —
| 2016-10-25 | Tue | Done: Wrote event system, refined objects, created level. eliminated some components I could not find use for yet. Next: Try to come up with the harder puzzle aspect of this. Still rather unrefined. Come up with new components to add and ad another mechanic. refine existing mechanics. Help: Everything. Anything. |  | Done: Wrote event system, refined objects, created level. eliminated some components I could not find use for yet. Next: Try to come up with the harder puzzle aspect of this. Still rather unrefined. Come up with new components to add and ad another mechanic. refine existing mechanics. Help: Everything. Anything.
| 2016-10-26 | Wed | Done: Desperately searching for ideas becuase I thought what I had was enough and then I saw the feedback and reviews of other people's work. Next: Try anything within my power to make this better Help: Everything |  | Done: Desperately searching for ideas becuase I thought what I had was enough and then I saw the feedback and reviews of other people's work. Next: Try anything within my power to make this better Help: Everything
| 2016-10-27 | Thu | Done: Pivoting. Doc appointments (sorry) Next: Try anything within my power to make this better Help: Everything
| 2016-10-28 | Fri | Done: -- Cast related stuff Next: -- Help: Everything
| 2016-10-29 | Sat | Done: Thought of better ideas. Sketches. Adding more framework. Gathering assets and various cool things. Next: Pivot. No Halloween :( Help: Everything
| 2016-10-30 | Sun | Done: Pivoted. Rewrote most of the assets. Gather music. Made some images Next: Try anything within my power to make this better. I made a lot of cool things. Help: Everything
| 2016-10-31 | Mon | Done: Pivoted. Levels. New assets Next: Trying other things plus. Getting used to cast still. Very slow process Help:--
| 2016-11-01 | Tue | Done: Almost done. need levels and UI Next: Fixing Help: --
| 2016-11-02 | Wed | Done: Pivoted. Rewrote most of the assets Next: Turin in? Help: --
| 2016-11-03 | Thu
| 2016-11-04 | Fri
| 2016-11-05 | Sat
| 2016-11-06 | Sun
| 2016-11-07 | Mon